## Sheet1
LANDIS-II Updates and Corrections Project
| Weekly Time Sheet for: | Vincent Schuster
| Week Beginning: | 2017-05-15
[6 empty] | Approx. % | Hrs
Task Set | Task | Task Description / Work Performed / Comments |  |  |  | Complete? | Worked
OV2 |  | Weekly Meeting |  |  |  | N/A | 1
GHB4 |  | Debugging Metadata for Extension-Dynamic-Biomass-Fire |  |  |  | 100% | 6
OV1 |  | Write-up on debugger and how to attach |  |  |  | 100% | 4.5
MT1 | Management Structure Design |  | OV1 | Basic Training
MT2 | Recruitment |  | OV2 | Mtgs
MT3 | Trainings
MT4 | Project Management
MT5 | QA/QC and Restructuring
[6 empty] | Total Hrs | 11.5
Employee Signature |  | Vincent Schuster (signature on file) |  | Date | 2017-05-21 | GHB1 = Core-Model
GHB2 = LANDVIZ
GHB3 = Extension-Base-Harvest
GHB4 = Extension-Biomass-Extension
Approval Signature |  |  |  | Date |  | GHB5 = MiscQuikFix (list repos)