## Sheet1
LANDIS-II Updates and Corrections Project
| Weekly Time Sheet for: | Vincent Schuster
| Week Beginning: | 2016-12-12
[6 empty] | Task | Approx. % | Hrs
Task Set | Task | Task Description / Work Performed / Comments |  |  |  | Leader? | Complete? | Worked
PRG
| OV1 | Explorations of Core-Model and Base-Harvest | [5 empty] | 5
| GHB1 | Removal of SDK |  |  |  |  | 100% | 3
| OV2 | Meeting with Rob (14 Dec 2016) | [5 empty] | 0.5
| GHB1 | Began work on core-model issue list |  |  |  |  | 0% | 1
MT1 | Management Structure |  | OV1 | Basic Training
MT2 | Recruitment |  | OV2 | Status Mtgs
MT3 | Trainings |  | OV3 | Specialty Training
MT4 | Project Management
MT5 | LANDIS-II code testing
[7 empty] | Total Hrs | 9.5
Employee Signature |  | Vincent Schuster (signature on file) |  | Date | 2016-12-18 | Freq. GitHub Branch Codes
[6 empty] | GHB1= | Core-Model
[6 empty] | GHB2 = | LANDVIZ-Development
[6 empty] | GHB3 = | Extension-Base-Harvest
Approval Signature |  |  |  | Date |  | GHB4 = | Extension-Biomass-Extension